W1NNR | W1NNR-998 | https://w1consultoria.atlassian.net/browse/W1NNR-998 | Assinaturas do S1nc exibirem na tela de assinatura do painel Admin | Tarefa | Concluído | 71112 | 2025-05-30 18:13:09 | 30/05/2025 | Danilo Monreal | Homolog | QA Approved Hml | qa approved hml | homolog | 4 | homolog | 2025-05-30 18:04:04 | 2025-05-30 21:10:36 | 4 |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0.12322
W1NNR | W1NNR-998 | https://w1consultoria.atlassian.net/browse/W1NNR-998 | Assinaturas do S1nc exibirem na tela de assinatura do painel Admin | Tarefa | Concluído | 71144 | 2025-05-30 21:10:36 | 30/05/2025 | Igor Rezende | QA Approved Hml | Ready To Staging | ready to staging | qa approved hml | 5 | qa approved hml | 2025-05-30 18:13:09 | 2025-05-30 21:11:23 | 5 | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0.00054596
W1NNR | W1NNR-998 | https://w1consultoria.atlassian.net/browse/W1NNR-998 | Assinaturas do S1nc exibirem na tela de assinatura do painel Admin | Tarefa | Concluído | 71160 | 2025-05-30 21:11:23 | 30/05/2025 | Igor Rezende | Ready To Staging | Staging | staging | ready to staging | 6 | ready to staging | 2025-05-30 21:10:36 | 2025-05-30 21:49:50 |  | 5 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0.026708
W1NNR | W1NNR-998 | https://w1consultoria.atlassian.net/browse/W1NNR-998 | Assinaturas do S1nc exibirem na tela de assinatura do painel Admin | Tarefa | Concluído | 71191 | 2025-05-30 21:49:50 | 30/05/2025 | Danilo Monreal | Staging | QA Approved Staging | qa approved staging | staging | 7 | staging | 2025-05-30 21:11:23 | 2025-06-02 14:16:14 | 7 |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2.685
W1NNR | W1NNR-998 | https://w1consultoria.atlassian.net/browse/W1NNR-998 | Assinaturas do S1nc exibirem na tela de assinatura do painel Admin | Tarefa | Concluído | 71249 | 2025-06-02 14:16:14 | 02/06/2025 | Lorraine Caribe | QA Approved Staging | Ready for Production | ready for production | qa approved staging | 8 | qa approved staging | 2025-05-30 21:49:50 | 2025-06-02 17:36:33 | 8 | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0.13911
W1NNR | W1NNR-998 | https://w1consultoria.atlassian.net/browse/W1NNR-998 | Assinaturas do S1nc exibirem na tela de assinatura do painel Admin | Tarefa | Concluído | 71298 | 2025-06-02 17:36:33 | 02/06/2025 | Lorraine Caribe | Ready for Production | Done | done | ready for production | 9 | ready for production | 2025-06-02 14:16:14 |  | 9 | 8 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE

## PM4PyDFGEdges
From | To | Count
Ready for Production | Done | 779
Ready To Staging | Staging | 694
Staging | QA Approved Staging | 563
QA Approved Staging | Ready for Production | 536
QA Approved Hml | Ready To Staging | 527
In Progress | Ready to Homolog | 495
Homolog | QA Approved Hml | 495
Ready to Homolog | Homolog | 494
In Progress | Ready To Staging | 152
in analytics | In Development | 127
In Progess | Ready for code review | 108
Staging | QA Approved | 103
Staging | Ready for Production | 103
Ready for code review | CODE REVIEW | 100
READY FOR DEVELOPMENT | In Progess | 99
Cancelled | Done | 97
QA Approved | Ready for Production | 90
CODE REVIEW | READY FOR TESTING/QA | 89
Backlog | READY FOR DEVELOPMENT | 80
READY FOR TESTING/QA | Testing / QA | 79
Testing / QA | Ready To Staging | 70
In Development | Staging | 67
In Staging | Ready for Production | 58
Backlog | In Progress | 56
QA Approved Staging | Done | 42
Triagem | Cancelled | 38
In Development | In Validation | 34
Homologation | QA Approved Hml | 27
Ready To Staging | In Staging | 27
In Progress | Ready for Staging | 26
Ready for Staging | Staging | 23
Production | Done | 22
In Validation | Done | 18
Backlog | Triagem | 17
Staging | Homologation | 17
In Development | In Staging | 15
Ready for Production | Production | 15
In Progress | Staging | 14
Triagem | Backlog | 14
Prioritized | Backlog | 12
Ready To Staging | ready for homolog | 12
ready for homolog | Ready To Staging | 12
Backlog | Cancelled | 12
QA Approved | Done | 11
In Staging | Prioritized | 11
Backlog | In Staging | 11
In Validation | QA Approved Staging | 11
Ready To Staging | Done | 10
Ready To Staging | Homologation | 10
CODE REVIEW | In Progess | 10
Staging | In Staging | 9
QA Approved | QA Approved Hml | 8
Approval | Backlog | 7
Testing / QA | In Progess | 7
Ready To Staging | Ready to Homologation | 6
In Progress | In Staging | 6
Staging | Done | 6
Ready to Analytics | Backlog | 5
Ready for code review | In Progess | 5
Ready to Homolog | READY FOR TESTING/QA | 5
To Do | Backlog | 5
In Progress | Cancelled | 5
In Progress | Production | 5
In Progess | Done | 5
In Validation | QA Approved | 5
QA Approved Hml | Ready to Analytics | 3
In Development | Ready for Production | 3
In Progress | Ready for Production | 3
Ready to Analytics | in analytics | 3
In Progress | Backlog | 3
Ready To Staging | Ready for Production | 3
To Do | In Progress | 3
Approval | Ready to Homolog | 3
Ready to Homologation | Homolog | 3
QA Approved | Staging | 3
In Development | Done | 3
In Validation | In Staging | 3
in analytics | Done | 3
In Development | In Progress | 3
Ready to Homologation | Ready to Analytics | 3
Ready to Analytics | Homolog | 2
Ready for Staging | Ready for Staging | 2
In Progress | Done | 2
In Validation | Ready for Production | 2
Staging | Production | 2
Done | QA Approved Staging | 2
To Do | Ready to Analytics | 2
in analytics | Backlog | 2
in analytics | In Validation | 2
Ready for Production | QA Approved Staging | 2
Ready to Analytics | Cancelled | 2
Homolog | Staging | 2
Ready To Staging | Ready To Staging | 2
Homolog | Cancelled | 2
In Development | QA Approved | 2
Ready To Staging | In Progress | 2
In Staging | Done | 2
Backlog do Produto | Triagem | 1
Backlog | Ready to Design | 1
Staging | Ready To Staging | 1
Backlog | Ready to Analytics | 1
Staging | in analytics | 1
Tech Review | Done | 1
Testing / QA | Done | 1
In Backlog | Backlog | 1
READY FOR DEVELOPMENT | Backlog | 1
In Progress | In Progress | 1
Ready for Production | QA Approved | 1
READY FOR TESTING/QA | Done | 1
In Development | Cancelled | 1
Backlog | Done | 1
In Progress | In Backlog | 1
Triagem | Done | 1
Production | in analytics | 1
in analytics | Cancelled | 1
In Development | Homolog | 1
Approval | Staging | 1
In Validation | in analytics | 1
in analytics | Ready for Production | 1
in analytics | Triagem | 1
In Development | Backlog | 1
Staging | In Progess | 1
Staging | In Progress | 1
In Validation | Tech Review | 1
Ready for Staging | In Progress | 1
Ready for Staging | Production | 1
Ready for Staging | Ready To Staging | 1
Homolog | Done | 1
Done | In Validation | 1
Ready for build | In Validation | 1
Done | Backlog | 1
In Progress | To Do | 1
In Development | Ready for build | 1
Ready to Analytics | Done | 1
Done | Ready for Production | 1
Ready to Analytics | Triagem | 1
Ready to Design | Ready to Analytics | 1
Cancelled | in analytics | 1
In Development | Ready to Homolog | 1
Homolog | In Progress | 1
Staging | Cancelled | 1
In Progress | Ready to Analytics | 1
Staging | Homolog | 1
Staging | In Development | 1
Ready for Production | Staging | 1

## PM4PyDFGPerfEdges
From | To | Count | PerfSeconds | PerfHours
Homolog | Done | 1 | 23573676.358 | 6548.2434
Backlog | Triagem | 17 | 16550678.0625 | 4597.4106
Cancelled | Done | 97 | 13342072.2386 | 3706.1312
In Progress | Done | 2 | 12081954.016 | 3356.0983
In Development | Backlog | 1 | 10293851.946 | 2859.4033
Staging | in analytics | 1 | 8995376.128 | 2498.7156
To Do | Ready to Analytics | 2 | 7969689.2995 | 2213.8026
To Do | Backlog | 5 | 7951269.0556 | 2208.6858
Done | Backlog | 1 | 7785043.006 | 2162.5119
In Development | Ready to Homolog | 1 | 6737375.112 | 1871.4931
Ready To Staging | Ready to Homologation | 6 | 4795235.0843 | 1332.0097
Ready to Homologation | Ready to Analytics | 3 | 4775160.5687 | 1326.4335
In Progress | Ready for Production | 3 | 3908356.049 | 1085.6545
Backlog | Cancelled | 12 | 3530034.8825 | 980.5652
QA Approved Hml | Ready to Analytics | 3 | 3047818.5467 | 846.6163
Production | in analytics | 1 | 2918862.228 | 810.7951
In Validation | Ready for Production | 2 | 2594598.335 | 720.7218
in analytics | Backlog | 2 | 2556669.1055 | 710.1859
In Progress | In Staging | 6 | 1844414.6958 | 512.3374
Ready To Staging | In Staging | 27 | 1832707.3555 | 509.0854
Ready for Staging | In Progress | 1 | 1622913.41 | 450.8093
Triagem | Done | 1 | 1557982.42 | 432.7729
Triagem | Cancelled | 38 | 1277746.7618 | 354.9297
Ready to Analytics | Triagem | 1 | 1214906.606 | 337.4741
In Progress | Production | 5 | 1198341.636 | 332.8727
Ready for Production | Staging | 1 | 1166809.955 | 324.1139
Staging | Homologation | 17 | 1116509.9807 | 310.1417
Ready To Staging | Ready for Production | 3 | 1073527.2157 | 298.202
Ready to Homolog | READY FOR TESTING/QA | 5 | 959384.7188 | 266.4958
Homologation | QA Approved Hml | 27 | 953099.5265 | 264.7499
Backlog | In Progress | 56 | 921517.2341 | 255.977
Staging | QA Approved | 103 | 827559.4374 | 229.8776
Ready for Staging | Ready for Staging | 2 | 822488.477 | 228.469
Staging | Homolog | 1 | 784520.012 | 217.9222
Production | Done | 22 | 752075.9893 | 208.91
Homolog | QA Approved Hml | 495 | 738349.9922 | 205.0972
Ready for Staging | Ready To Staging | 1 | 716559.047 | 199.0442
In Progress | Cancelled | 5 | 692265.4694 | 192.296
To Do | In Progress | 3 | 676945.19 | 188.0403
In Progress | Ready To Staging | 152 | 668743.205 | 185.762
Ready to Analytics | in analytics | 3 | 657557.4773 | 182.6549
Ready for Staging | Staging | 23 | 654972.297 | 181.9367
In Progress | Backlog | 3 | 632102.1747 | 175.5839
Approval | Backlog | 7 | 609402.7973 | 169.2786
In Validation | Tech Review | 1 | 609206.645 | 169.2241
Ready to Design | Ready to Analytics | 1 | 601695.514 | 167.1376
Ready to Analytics | Cancelled | 2 | 599855.4155 | 166.6265
READY FOR TESTING/QA | Done | 1 | 568129.066 | 157.8136
Testing / QA | In Progess | 7 | 544127.9684 | 151.1467
Ready To Staging | Homologation | 10 | 521496.5965 | 144.8602
Ready To Staging | ready for homolog | 12 | 508962.4064 | 141.3784
In Staging | Prioritized | 11 | 506373.3715 | 140.6593
Ready To Staging | Done | 10 | 458139.4449 | 127.261
In Progess | Done | 5 | 445831.1286 | 123.842
In Progress | Staging | 14 | 440485.5431 | 122.3571
Homolog | Cancelled | 2 | 428281.0235 | 118.967
QA Approved | Ready for Production | 90 | 427272.2881 | 118.6867
in analytics | Triagem | 1 | 423353.933 | 117.5983
In Staging | Ready for Production | 58 | 419385.2182 | 116.4959
QA Approved Hml | Ready To Staging | 527 | 416952.5458 | 115.8202
Homolog | Staging | 2 | 410462.116 | 114.0173
Ready to Homolog | Homolog | 494 | 403305.4401 | 112.0293
Done | In Validation | 1 | 395037.444 | 109.7326
Ready for Production | Production | 15 | 369229.3265 | 102.5637
Triagem | Backlog | 14 | 368292.1545 | 102.3034
In Progress | Ready for Staging | 26 | 354068.0468 | 98.3522
In Validation | Done | 18 | 349212.9879 | 97.0036
QA Approved | Done | 11 | 340162.8654 | 94.4897
Tech Review | Done | 1 | 333910.208 | 92.7528
In Progress | Ready to Homolog | 495 | 330487.5725 | 91.8021
Approval | Staging | 1 | 319572.577 | 88.7702
Ready for code review | In Progess | 5 | 280179.5736 | 77.8277
Approval | Ready to Homolog | 3 | 262748.913 | 72.9858
In Validation | In Staging | 3 | 225659.6573 | 62.6832
READY FOR DEVELOPMENT | In Progess | 99 | 208767.1833 | 57.9909
Ready to Analytics | Backlog | 5 | 205637.2784 | 57.1215
Backlog | Ready to Analytics | 1 | 200907.444 | 55.8076
Ready for Staging | Production | 1 | 195473.428 | 54.2982
Testing / QA | Ready To Staging | 70 | 191136.8358 | 53.0936
Ready to Analytics | Done | 1 | 183090.815 | 50.8586
READY FOR TESTING/QA | Testing / QA | 79 | 182078.096 | 50.5772
Ready To Staging | Staging | 694 | 180924.691 | 50.2569
In Backlog | Backlog | 1 | 180842.301 | 50.234
in analytics | Done | 3 | 170904.1417 | 47.4734
In Progess | Ready for code review | 108 | 159833.2047 | 44.3981
In Development | In Staging | 15 | 159668.369 | 44.3523
in analytics | In Validation | 2 | 154666.0555 | 42.9628
In Development | Done | 3 | 136102.8823 | 37.8064
In Development | Staging | 67 | 134984.1353 | 37.4956
In Development | Ready for Production | 3 | 134196.6393 | 37.2768
In Validation | QA Approved Staging | 11 | 130689.0005 | 36.3025
Ready for Production | Done | 779 | 127967.2599 | 35.5465
In Staging | Done | 2 | 125402.122 | 34.8339
in analytics | In Development | 127 | 121479.1095 | 33.7442
QA Approved Staging | Ready for Production | 536 | 116007.9573 | 32.2244
CODE REVIEW | In Progess | 10 | 113554.7567 | 31.543
Staging | Ready for Production | 103 | 112272.1933 | 31.1867
Staging | In Staging | 9 | 106184.8731 | 29.4958
Testing / QA | Done | 1 | 100486.806 | 27.913
In Development | In Validation | 34 | 100188.8172 | 27.8302
CODE REVIEW | READY FOR TESTING/QA | 89 | 97616.4292 | 27.1157
In Development | In Progress | 3 | 92031.4383 | 25.5643
QA Approved Staging | Done | 42 | 91618.2009 | 25.4495
Staging | Done | 6 | 90093.3692 | 25.0259
Staging | QA Approved Staging | 563 | 88373.0377 | 24.5481
In Development | Ready for build | 1 | 85086.572 | 23.6352
Done | QA Approved Staging | 2 | 83357.6345 | 23.1549
Staging | In Progess | 1 | 75723.274 | 21.0342
In Development | QA Approved | 2 | 68545.359 | 19.0404
In Progress | Ready to Analytics | 1 | 68377.873 | 18.9939
QA Approved | QA Approved Hml | 8 | 67798.8585 | 18.833
Staging | Production | 2 | 62591.2185 | 17.3864
Backlog | Ready to Design | 1 | 50691.184 | 14.0809
in analytics | Ready for Production | 1 | 46444.054 | 12.9011
Backlog | READY FOR DEVELOPMENT | 80 | 45042.7949 | 12.5119
In Validation | QA Approved | 5 | 41152.5016 | 11.4313
Ready for code review | CODE REVIEW | 100 | 38748.3017 | 10.7634
In Development | Cancelled | 1 | 36605.789 | 10.1683
In Development | Homolog | 1 | 22973.717 | 6.3816
ready for homolog | Ready To Staging | 12 | 18262.354 | 5.0729
Ready to Homologation | Homolog | 3 | 16114.2207 | 4.4762
Staging | Cancelled | 1 | 14057.995 | 3.905
in analytics | Cancelled | 1 | 7532.323 | 2.0923
Ready To Staging | Ready To Staging | 2 | 5434.004 | 1.5094
In Progress | To Do | 1 | 660.437 | 0.18345
Done | Ready for Production | 1 | 471.394 | 0.13094
QA Approved | Staging | 3 | 444.4617 | 0.12346
Prioritized | Backlog | 12 | 277.6896 | 0.077136
Backlog do Produto | Triagem | 1 | 248.476 | 0.069021
Homolog | In Progress | 1 | 222.611 | 0.061836
In Progress | In Progress | 1 | 202.84 | 0.056344
Backlog | In Staging | 11 | 145.1816 | 0.040328
In Validation | in analytics | 1 | 119.01 | 0.033058
In Progress | In Backlog | 1 | 102.46 | 0.028461
Ready to Analytics | Homolog | 2 | 43.8535 | 0.012182
Staging | Ready To Staging | 1 | 38.993 | 0.010831
Staging | In Development | 1 | 21.365 | 0.0059347
Ready To Staging | In Progress | 2 | 19.292 | 0.0053589
Cancelled | in analytics | 1 | 18.246 | 0.0050683
Staging | In Progress | 1 | 16.51 | 0.0045861
Ready for Production | QA Approved Staging | 2 | 6.8515 | 0.0019032
Ready for Production | QA Approved | 1 | 3.56 | 0.00098889
Backlog | Done | 1 | 3.453 | 0.00095917
Ready for build | In Validation | 1 | 3.286 | 0.00091278
READY FOR DEVELOPMENT | Backlog | 1 | 2.518 | 0.00069944

## PM4PyTBRResumo
Metric | Value
num_cases | 1055
perc_fit_traces | 100
average_trace_fitness | 1
min_trace_fitness | 1

## PM4PyTBRCasos
Issue Key | TraceIsFit | TraceFitness | MissingTokens | RemainingTokens | ConsumedTokens | ProducedTokens
W1NNR-1003 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1004 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-1007 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-1008 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1009 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1014 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1015 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1017 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1018 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1019 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1020 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1021 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1022 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1023 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1024 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1025 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1026 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1027 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1028 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1029 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1030 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1031 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1032 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1033 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1036 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1040 | TRUE | 1 | 0 | 0 | 81 | 81
W1NNR-1041 | TRUE | 1 | 0 | 0 | 81 | 81
W1NNR-1043 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1045 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1046 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-105 | TRUE | 1 | 0 | 0 | 44 | 44
W1NNR-1051 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-1055 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1058 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-106 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-1061 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1062 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1064 | TRUE | 1 | 0 | 0 | 16 | 16
W1NNR-1065 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1066 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1067 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1068 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-1069 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-107 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1070 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1071 | TRUE | 1 | 0 | 0 | 81 | 81
W1NNR-1072 | TRUE | 1 | 0 | 0 | 81 | 81
W1NNR-1073 | TRUE | 1 | 0 | 0 | 41 | 41
W1NNR-1074 | TRUE | 1 | 0 | 0 | 81 | 81
W1NNR-1076 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1077 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1079 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-108 | TRUE | 1 | 0 | 0 | 44 | 44
W1NNR-1080 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1081 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1082 | TRUE | 1 | 0 | 0 | 75 | 75
W1NNR-1083 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1085 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1087 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-109 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-1090 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-1093 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-110 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-1102 | TRUE | 1 | 0 | 0 | 96 | 96
W1NNR-1109 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1110 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1111 | TRUE | 1 | 0 | 0 | 81 | 81
W1NNR-1117 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1118 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1119 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1120 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1121 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1122 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1123 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1124 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1125 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1126 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1127 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1128 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1129 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1133 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1134 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1149 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1150 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1151 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1155 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1156 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1157 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1162 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1163 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1166 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1167 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1168 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-1169 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1170 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1171 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1188 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1189 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1191 | TRUE | 1 | 0 | 0 | 81 | 81
W1NNR-1192 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1193 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1194 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1195 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1199 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-12 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-1200 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1201 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1202 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1208 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1209 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-121 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-1214 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1215 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1226 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1230 | TRUE | 1 | 0 | 0 | 69 | 69
W1NNR-1231 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1238 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1239 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-124 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-1240 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1241 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1242 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1246 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1247 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1248 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1253 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1254 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1260 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1262 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1263 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1264 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1265 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1266 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1267 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1268 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1269 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-127 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-1270 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1271 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1272 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1273 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1274 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1277 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1279 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1282 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1284 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1285 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1286 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1294 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-1295 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-1296 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-1297 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-1299 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-13 | TRUE | 1 | 0 | 0 | 60 | 60
W1NNR-1303 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1305 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1307 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1308 | TRUE | 1 | 0 | 0 | 85 | 85
W1NNR-1312 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1313 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1314 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1325 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1326 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1327 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1328 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1329 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1333 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1335 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1337 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1338 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1339 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1340 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1341 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1345 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1346 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1347 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1351 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1352 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1353 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1356 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1357 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1359 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1360 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1361 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1362 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1363 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1364 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1366 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1367 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1368 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1369 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1371 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1372 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1373 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1374 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1375 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1390 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1391 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1396 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-14 | TRUE | 1 | 0 | 0 | 58 | 58
W1NNR-1400 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1401 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1402 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1403 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1404 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1406 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-1407 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1408 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-1410 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1412 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1414 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1415 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1417 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1418 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1419 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1424 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1431 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1433 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1434 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1436 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1437 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1438 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1446 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1461 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1462 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1465 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1472 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1473 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1479 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1499 | TRUE | 1 | 0 | 0 | 94 | 94
W1NNR-15 | TRUE | 1 | 0 | 0 | 58 | 58
W1NNR-1500 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-1508 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1509 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1511 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1514 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1515 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1516 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1517 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1518 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1522 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1546 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1550 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1552 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1555 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1556 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1557 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1558 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1559 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1560 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1561 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1562 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1563 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1564 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1565 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1566 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1567 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1568 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1569 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1570 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1571 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1572 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1573 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1574 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1575 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1576 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1577 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1578 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1579 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1580 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1581 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1582 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1583 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1584 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1585 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1586 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1587 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1588 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1589 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1590 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1591 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1592 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1593 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1594 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1595 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1596 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1597 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1599 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1600 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1601 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1602 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1603 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1604 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1605 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1606 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1607 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1608 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1609 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1610 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1611 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1612 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1613 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1614 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1617 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1630 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1633 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1634 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1639 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1640 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1641 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1642 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1643 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1644 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1645 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1646 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1647 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1648 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1649 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1650 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1651 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1652 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1653 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1654 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1655 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1656 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1657 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1658 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1659 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1660 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1661 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1662 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1663 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1664 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1665 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1666 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1667 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1668 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1669 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1670 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1671 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1672 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1673 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1674 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1675 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1676 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-168 | TRUE | 1 | 0 | 0 | 41 | 41
W1NNR-1684 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1685 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1689 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-1693 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1697 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-1698 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-1703 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1707 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1714 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1715 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1716 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-1717 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1718 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1719 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-1720 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1721 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1722 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1723 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1724 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1725 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1727 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1728 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1729 | TRUE | 1 | 0 | 0 | 69 | 69
W1NNR-173 | TRUE | 1 | 0 | 0 | 30 | 30
W1NNR-1730 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1738 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-174 | TRUE | 1 | 0 | 0 | 30 | 30
W1NNR-1740 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1743 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1745 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1749 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-175 | TRUE | 1 | 0 | 0 | 30 | 30
W1NNR-1750 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1751 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1753 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1754 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1755 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1756 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1757 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1759 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1760 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1761 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-1764 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1767 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1768 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-177 | TRUE | 1 | 0 | 0 | 30 | 30
W1NNR-1771 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1777 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1778 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-178 | TRUE | 1 | 0 | 0 | 23 | 23
W1NNR-1783 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1784 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1785 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1787 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1790 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1791 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1794 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1796 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1797 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1802 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1803 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1804 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-1805 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1806 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1807 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1808 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1809 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1814 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1819 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1823 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1824 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1826 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1834 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1836 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1839 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1840 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1844 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1850 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1851 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1855 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1857 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1860 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1861 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1863 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1864 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1865 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1867 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1869 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1870 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1871 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1872 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1873 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1874 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1875 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1876 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1878 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1880 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-1881 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1882 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1885 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1886 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1888 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1889 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1890 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1891 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1892 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1893 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1894 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1895 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1896 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1897 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1898 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1899 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1900 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1901 | TRUE | 1 | 0 | 0 | 75 | 75
W1NNR-1905 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1907 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1922 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1924 | TRUE | 1 | 0 | 0 | 73 | 73
W1NNR-1925 | TRUE | 1 | 0 | 0 | 73 | 73
W1NNR-1926 | TRUE | 1 | 0 | 0 | 73 | 73
W1NNR-1927 | TRUE | 1 | 0 | 0 | 73 | 73
W1NNR-1933 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1934 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1935 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1936 | TRUE | 1 | 0 | 0 | 73 | 73
W1NNR-1937 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-1938 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1939 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1940 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1956 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1957 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1958 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1959 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1960 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1961 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1962 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1963 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1964 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1965 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1966 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1968 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1972 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1974 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1975 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1976 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1979 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1980 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1981 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1982 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1986 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1990 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-1991 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-1992 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-2 | TRUE | 1 | 0 | 0 | 63 | 63
W1NNR-20 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-2003 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-2005 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-2006 | TRUE | 1 | 0 | 0 | 71 | 71
W1NNR-2007 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-2008 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-2009 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-201 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-2010 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-2011 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-2012 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-2016 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2027 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-2028 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-2029 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-2030 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-2033 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-2036 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-2037 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-2038 | TRUE | 1 | 0 | 0 | 75 | 75
W1NNR-2039 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-2040 | TRUE | 1 | 0 | 0 | 69 | 69
W1NNR-2042 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2044 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2045 | TRUE | 1 | 0 | 0 | 61 | 61
W1NNR-2046 | TRUE | 1 | 0 | 0 | 50 | 50
W1NNR-2047 | TRUE | 1 | 0 | 0 | 57 | 57
W1NNR-2048 | TRUE | 1 | 0 | 0 | 66 | 66
W1NNR-2049 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-2050 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-2051 | TRUE | 1 | 0 | 0 | 54 | 54
W1NNR-2052 | TRUE | 1 | 0 | 0 | 57 | 57
W1NNR-2055 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-2056 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-2057 | TRUE | 1 | 0 | 0 | 57 | 57
W1NNR-2079 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-2082 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-2083 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-2084 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-2085 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-2098 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-2099 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-21 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-2104 | TRUE | 1 | 0 | 0 | 100 | 100
W1NNR-2110 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-2111 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-2112 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-2116 | TRUE | 1 | 0 | 0 | 71 | 71
W1NNR-2120 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-2124 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2136 | TRUE | 1 | 0 | 0 | 75 | 75
W1NNR-2144 | TRUE | 1 | 0 | 0 | 94 | 94
W1NNR-2147 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2157 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2161 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2162 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-217 | TRUE | 1 | 0 | 0 | 70 | 70
W1NNR-2172 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2173 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2174 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-2181 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2182 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2183 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-2186 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2188 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-2192 | TRUE | 1 | 0 | 0 | 62 | 62
W1NNR-2199 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-22 | TRUE | 1 | 0 | 0 | 58 | 58
W1NNR-220 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-2200 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2201 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-2203 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-2205 | TRUE | 1 | 0 | 0 | 16 | 16
W1NNR-2206 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-2207 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-2208 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2212 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2213 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2214 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2216 | TRUE | 1 | 0 | 0 | 72 | 72
W1NNR-2217 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-2218 | TRUE | 1 | 0 | 0 | 70 | 70
W1NNR-2219 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-2220 | TRUE | 1 | 0 | 0 | 63 | 63
W1NNR-2222 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2223 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-2226 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-2227 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-2234 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2240 | TRUE | 1 | 0 | 0 | 71 | 71
W1NNR-2247 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2248 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2249 | TRUE | 1 | 0 | 0 | 57 | 57
W1NNR-225 | TRUE | 1 | 0 | 0 | 30 | 30
W1NNR-2250 | TRUE | 1 | 0 | 0 | 16 | 16
W1NNR-2251 | TRUE | 1 | 0 | 0 | 16 | 16
W1NNR-2252 | TRUE | 1 | 0 | 0 | 16 | 16
W1NNR-2253 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2255 | TRUE | 1 | 0 | 0 | 4 | 4
W1NNR-2257 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2258 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-2259 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-226 | TRUE | 1 | 0 | 0 | 30 | 30
W1NNR-2260 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2262 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2265 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2266 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2268 | TRUE | 1 | 0 | 0 | 4 | 4
W1NNR-227 | TRUE | 1 | 0 | 0 | 44 | 44
W1NNR-2270 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-2271 | TRUE | 1 | 0 | 0 | 11 | 11
W1NNR-2272 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-2276 | TRUE | 1 | 0 | 0 | 61 | 61
W1NNR-2277 | TRUE | 1 | 0 | 0 | 57 | 57
W1NNR-2278 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-228 | TRUE | 1 | 0 | 0 | 48 | 48
W1NNR-2280 | TRUE | 1 | 0 | 0 | 57 | 57
W1NNR-2281 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-2283 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-2284 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-2285 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-2286 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-2288 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-2289 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-2290 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-2291 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2297 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-23 | TRUE | 1 | 0 | 0 | 57 | 57
W1NNR-230 | TRUE | 1 | 0 | 0 | 46 | 46
W1NNR-2301 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-2302 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2304 | TRUE | 1 | 0 | 0 | 61 | 61
W1NNR-2306 | TRUE | 1 | 0 | 0 | 60 | 60
W1NNR-2307 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-231 | TRUE | 1 | 0 | 0 | 42 | 42
W1NNR-2314 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-2315 | TRUE | 1 | 0 | 0 | 57 | 57
W1NNR-2319 | TRUE | 1 | 0 | 0 | 16 | 16
W1NNR-232 | TRUE | 1 | 0 | 0 | 42 | 42
W1NNR-2320 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2321 | TRUE | 1 | 0 | 0 | 4 | 4
W1NNR-2322 | TRUE | 1 | 0 | 0 | 16 | 16
W1NNR-2324 | TRUE | 1 | 0 | 0 | 67 | 67
W1NNR-2326 | TRUE | 1 | 0 | 0 | 64 | 64
W1NNR-2327 | TRUE | 1 | 0 | 0 | 4 | 4
W1NNR-233 | TRUE | 1 | 0 | 0 | 42 | 42
W1NNR-2339 | TRUE | 1 | 0 | 0 | 65 | 65
W1NNR-234 | TRUE | 1 | 0 | 0 | 42 | 42
W1NNR-2341 | TRUE | 1 | 0 | 0 | 66 | 66
W1NNR-236 | TRUE | 1 | 0 | 0 | 44 | 44
W1NNR-237 | TRUE | 1 | 0 | 0 | 44 | 44
W1NNR-238 | TRUE | 1 | 0 | 0 | 44 | 44
W1NNR-239 | TRUE | 1 | 0 | 0 | 44 | 44
W1NNR-24 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-240 | TRUE | 1 | 0 | 0 | 44 | 44
W1NNR-242 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-243 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-244 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-25 | TRUE | 1 | 0 | 0 | 57 | 57
W1NNR-251 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-252 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-253 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-255 | TRUE | 1 | 0 | 0 | 45 | 45
W1NNR-258 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-26 | TRUE | 1 | 0 | 0 | 57 | 57
W1NNR-262 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-265 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-27 | TRUE | 1 | 0 | 0 | 57 | 57
W1NNR-28 | TRUE | 1 | 0 | 0 | 16 | 16
W1NNR-29 | TRUE | 1 | 0 | 0 | 51 | 51
W1NNR-30 | TRUE | 1 | 0 | 0 | 51 | 51
W1NNR-305 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-307 | TRUE | 1 | 0 | 0 | 16 | 16
W1NNR-31 | TRUE | 1 | 0 | 0 | 35 | 35
W1NNR-310 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-318 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-33 | TRUE | 1 | 0 | 0 | 51 | 51
W1NNR-331 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-35 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-353 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-358 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-36 | TRUE | 1 | 0 | 0 | 57 | 57
W1NNR-361 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-37 | TRUE | 1 | 0 | 0 | 57 | 57
W1NNR-374 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-376 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-378 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-379 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-385 | TRUE | 1 | 0 | 0 | 44 | 44
W1NNR-386 | TRUE | 1 | 0 | 0 | 44 | 44
W1NNR-387 | TRUE | 1 | 0 | 0 | 40 | 40
W1NNR-389 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-39 | TRUE | 1 | 0 | 0 | 57 | 57
W1NNR-391 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-392 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-393 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-396 | TRUE | 1 | 0 | 0 | 40 | 40
W1NNR-4 | TRUE | 1 | 0 | 0 | 86 | 86
W1NNR-40 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-400 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-406 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-407 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-408 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-409 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-41 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-410 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-411 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-412 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-413 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-414 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-415 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-416 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-417 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-418 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-419 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-42 | TRUE | 1 | 0 | 0 | 57 | 57
W1NNR-420 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-421 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-422 | TRUE | 1 | 0 | 0 | 58 | 58
W1NNR-423 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-424 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-425 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-426 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-427 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-428 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-429 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-43 | TRUE | 1 | 0 | 0 | 51 | 51
W1NNR-430 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-431 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-432 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-437 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-438 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-439 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-440 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-441 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-442 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-443 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-444 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-445 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-446 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-449 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-45 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-450 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-46 | TRUE | 1 | 0 | 0 | 51 | 51
W1NNR-466 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-47 | TRUE | 1 | 0 | 0 | 51 | 51
W1NNR-471 | TRUE | 1 | 0 | 0 | 48 | 48
W1NNR-472 | TRUE | 1 | 0 | 0 | 48 | 48
W1NNR-473 | TRUE | 1 | 0 | 0 | 48 | 48
W1NNR-474 | TRUE | 1 | 0 | 0 | 48 | 48
W1NNR-475 | TRUE | 1 | 0 | 0 | 48 | 48
W1NNR-476 | TRUE | 1 | 0 | 0 | 48 | 48
W1NNR-477 | TRUE | 1 | 0 | 0 | 48 | 48
W1NNR-478 | TRUE | 1 | 0 | 0 | 48 | 48
W1NNR-479 | TRUE | 1 | 0 | 0 | 48 | 48
W1NNR-48 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-480 | TRUE | 1 | 0 | 0 | 48 | 48
W1NNR-481 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-482 | TRUE | 1 | 0 | 0 | 48 | 48
W1NNR-483 | TRUE | 1 | 0 | 0 | 37 | 37
W1NNR-484 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-485 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-486 | TRUE | 1 | 0 | 0 | 72 | 72
W1NNR-487 | TRUE | 1 | 0 | 0 | 72 | 72
W1NNR-488 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-489 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-49 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-490 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-491 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-492 | TRUE | 1 | 0 | 0 | 72 | 72
W1NNR-493 | TRUE | 1 | 0 | 0 | 72 | 72
W1NNR-494 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-495 | TRUE | 1 | 0 | 0 | 72 | 72
W1NNR-496 | TRUE | 1 | 0 | 0 | 70 | 70
W1NNR-5 | TRUE | 1 | 0 | 0 | 72 | 72
W1NNR-50 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-500 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-502 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-503 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-505 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-506 | TRUE | 1 | 0 | 0 | 100 | 100
W1NNR-507 | TRUE | 1 | 0 | 0 | 100 | 100
W1NNR-508 | TRUE | 1 | 0 | 0 | 100 | 100
W1NNR-51 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-510 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-511 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-513 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-515 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-523 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-524 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-525 | TRUE | 1 | 0 | 0 | 72 | 72
W1NNR-532 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-533 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-534 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-54 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-55 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-56 | TRUE | 1 | 0 | 0 | 58 | 58
W1NNR-567 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-568 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-569 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-57 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-570 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-571 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-572 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-573 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-574 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-575 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-576 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-577 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-578 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-579 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-58 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-580 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-581 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-582 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-583 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-584 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-585 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-586 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-587 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-588 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-589 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-59 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-590 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-591 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-592 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-593 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-594 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-595 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-596 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-597 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-598 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-599 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-6 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-60 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-600 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-601 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-602 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-603 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-604 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-605 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-606 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-61 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-610 | TRUE | 1 | 0 | 0 | 68 | 68
W1NNR-611 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-612 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-613 | TRUE | 1 | 0 | 0 | 54 | 54
W1NNR-614 | TRUE | 1 | 0 | 0 | 54 | 54
W1NNR-615 | TRUE | 1 | 0 | 0 | 54 | 54
W1NNR-616 | TRUE | 1 | 0 | 0 | 54 | 54
W1NNR-617 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-618 | TRUE | 1 | 0 | 0 | 54 | 54
W1NNR-619 | TRUE | 1 | 0 | 0 | 54 | 54
W1NNR-620 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-621 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-622 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-623 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-624 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-625 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-626 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-627 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-628 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-629 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-63 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-630 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-631 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-632 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-633 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-634 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-635 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-636 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-641 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-642 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-649 | TRUE | 1 | 0 | 0 | 72 | 72
W1NNR-65 | TRUE | 1 | 0 | 0 | 61 | 61
W1NNR-651 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-655 | TRUE | 1 | 0 | 0 | 72 | 72
W1NNR-658 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-66 | TRUE | 1 | 0 | 0 | 59 | 59
W1NNR-664 | TRUE | 1 | 0 | 0 | 102 | 102
W1NNR-665 | TRUE | 1 | 0 | 0 | 96 | 96
W1NNR-672 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-680 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-686 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-687 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-691 | TRUE | 1 | 0 | 0 | 16 | 16
W1NNR-694 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-695 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-696 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-698 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-699 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-7 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-702 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-704 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-711 | TRUE | 1 | 0 | 0 | 44 | 44
W1NNR-712 | TRUE | 1 | 0 | 0 | 44 | 44
W1NNR-713 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-714 | TRUE | 1 | 0 | 0 | 44 | 44
W1NNR-715 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-716 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-717 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-720 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-723 | TRUE | 1 | 0 | 0 | 96 | 96
W1NNR-725 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-73 | TRUE | 1 | 0 | 0 | 44 | 44
W1NNR-730 | TRUE | 1 | 0 | 0 | 40 | 40
W1NNR-747 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-748 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-749 | TRUE | 1 | 0 | 0 | 72 | 72
W1NNR-75 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-76 | TRUE | 1 | 0 | 0 | 44 | 44
W1NNR-760 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-762 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-763 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-766 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-768 | TRUE | 1 | 0 | 0 | 55 | 55
W1NNR-77 | TRUE | 1 | 0 | 0 | 70 | 70
W1NNR-771 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-773 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-778 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-779 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-783 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-786 | TRUE | 1 | 0 | 0 | 86 | 86
W1NNR-80 | TRUE | 1 | 0 | 0 | 44 | 44
W1NNR-800 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-802 | TRUE | 1 | 0 | 0 | 74 | 74
W1NNR-803 | TRUE | 1 | 0 | 0 | 88 | 88
W1NNR-821 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-824 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-825 | TRUE | 1 | 0 | 0 | 84 | 84
W1NNR-826 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-827 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-829 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-830 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-833 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-834 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-835 | TRUE | 1 | 0 | 0 | 78 | 78
W1NNR-841 | TRUE | 1 | 0 | 0 | 85 | 85
W1NNR-842 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-843 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-844 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-845 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-846 | TRUE | 1 | 0 | 0 | 75 | 75
W1NNR-847 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-848 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-849 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-850 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-851 | TRUE | 1 | 0 | 0 | 75 | 75
W1NNR-852 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-853 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-855 | TRUE | 1 | 0 | 0 | 86 | 86
W1NNR-858 | TRUE | 1 | 0 | 0 | 76 | 76
W1NNR-859 | TRUE | 1 | 0 | 0 | 75 | 75
W1NNR-860 | TRUE | 1 | 0 | 0 | 77 | 77
W1NNR-861 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-862 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-863 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-866 | TRUE | 1 | 0 | 0 | 58 | 58
W1NNR-867 | TRUE | 1 | 0 | 0 | 81 | 81
W1NNR-869 | TRUE | 1 | 0 | 0 | 81 | 81
W1NNR-872 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-873 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-874 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-875 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-876 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-877 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-878 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-879 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-880 | TRUE | 1 | 0 | 0 | 56 | 56
W1NNR-881 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-882 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-883 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-884 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-885 | TRUE | 1 | 0 | 0 | 86 | 86
W1NNR-886 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-887 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-895 | TRUE | 1 | 0 | 0 | 82 | 82
W1NNR-897 | TRUE | 1 | 0 | 0 | 75 | 75
W1NNR-902 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-903 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-904 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-905 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-906 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-907 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-908 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-909 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-910 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-911 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-912 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-913 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-914 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-917 | TRUE | 1 | 0 | 0 | 102 | 102
W1NNR-918 | TRUE | 1 | 0 | 0 | 90 | 90
W1NNR-921 | TRUE | 1 | 0 | 0 | 96 | 96
W1NNR-922 | TRUE | 1 | 0 | 0 | 69 | 69
W1NNR-923 | TRUE | 1 | 0 | 0 | 23 | 23
W1NNR-928 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-929 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-930 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-931 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-932 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-933 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-934 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-935 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-936 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-937 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-938 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-939 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-940 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-941 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-942 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-943 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-944 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-945 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-946 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-947 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-948 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-949 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-950 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-951 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-952 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-953 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-954 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-955 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-956 | TRUE | 1 | 0 | 0 | 53 | 53
W1NNR-961 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-962 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-963 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-964 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-965 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-966 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-967 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-968 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-969 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-970 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-971 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-972 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-973 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-974 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-975 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-976 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-977 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-978 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-979 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-980 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-981 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-982 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-984 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-988 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-991 | TRUE | 1 | 0 | 0 | 80 | 80
W1NNR-992 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-993 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-996 | TRUE | 1 | 0 | 0 | 79 | 79
W1NNR-998 | TRUE | 1 | 0 | 0 | 79 | 79